## BookApp-Product Backlog(Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| BOOK-APP:001 | 1 | Registration of new user CRUD | Prathamesh | 2020-09-22 | 26 Sept,2020 |  | Completed
| BOOK-APP:002 | 2 | Book-List CRUD | Chinmay | 2020-09-22 | 26 Sept,2020 |  | Completed
| BOOK-APP:003 | 3 | User Comments CRUD | Srujana | 2020-09-22 | 26 Sept,2020 |  | Completed
Note on A1: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B1: This column is used to document the Use Case Identifier.
Note on D1: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E1: List the Scrum team members assigned to this task.
Note on F1: Column is used to document the date the task was assigned
Note on G1: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H1: Adjusted estimate after the Sprint has begun
Note on I1: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J1: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K1: Use this column to provide supporting information such as changes to the original requirement.
Note on M1: This column is used to link the requirements to any resulting modules (software).
Note on N1: This column is used to link the requirements/use cases to the test scenarios.
Note on O1: This column is used to link the requirements/use cases to the test scenarios.
Note on P1: This column is used to link the requirements/use cases to the test scenarios.